Laboratory safety audits a game changer in infection prevention and control

Duncan Ongayi

Chulaimbo County Hospital, Kenya

Abstract

Background: Facility and Biosafety is one of the quality system essentials envisaged in the Kenya Quality Manual for medical laboratories. ISO 15189-2012 Management clause 4.12 (continual improvement) stipulates that a laboratory shall participate in improvement project activities and laboratory shall conduct internal audits at planned intervals to identify nonconforming activities and institute corrective/preventive actions. Safety requirements are also highlighted in Section 12 (Facility and Biosafety) of WHO SLIPTA assessment checklist for clinical and health laboratories undergoing through ISO Accreditation. Chulaimbo County Hospital Laboratory in Kisumu west sub County, Kisumu County begun the journey of ISO Accreditation in October 2016 through mentorship by Global Health Solutions (GHS).

Problem statement: Baseline safety audit conducted in October 2016 while exit audit was in April 2019, baseline audit indicated low scores (18%). In view of this, Chulaimbo County Hospital laboratory embarked on this project to ensure compliance with this section requirement with the ultimate goal of improving safety, infection prevention and control and finally ISO Accreditation.

Methods: Baseline safety Laboratory audits were conducted using section 12 of the WHO SLIPTA observational assessment checklist. Action plan with strict timelines were developed with the primary goal being closing the gaps identified during the audits. Laboratory management appointed a safety focal person whose primary role was to spearhead closure of the nonconformities. Three follow up audits were thereafter conducted at an interval of one, three and four months respectively.

Results: The key findings identified were: 18% score at baseline with waste coming, no annual medical surveillance and Hepatitis B vaccination to staff, no first aid/spill kits and emergency eye wash/showers, no safety audits conducted, no incidences and occurrences investigated, laboratory staffs not all trained on biosafety/biosecurity, no safety sops developed, sample transporters not trained on biosafety and no clear policies on PEP among others. 58% score in audit one, 95% score in audit two and 98% score at third audit.

Key findings: Baseline (18%), First Audit (58%), Second Audit (95%), Exit Audit (98%).

Conclusion: There was a tremendous progress noted from 2016 (18%) to 2019 (98%) with regards to SLIPTA scores and ultimately the laboratory safety. Laboratory safety audit is an essential component of IPC in clinical and public health laboratories. It was also an important tool that can be used to mobilize resources for laboratory improvement and ultimately resulting in safe conducive and friendly laboratory working environment. Consistent mentorships on biosafety/biosecurity activities are a key and should be implemented in labs implementing ISO 15189:2012 accreditation.

Biography

Duncan Ongayi is Medical laboratory officer at Chulaimbo County Hospital, North West Kisumu, Kisumu West, Kisumu, Kenya.