## Slide 1: About OMICS Group
OMICS Group is an amalgamation of Open Access Publications and worldwide international science conferences and events. Established in the year 2007 with the sole aim of making the information on Sciences and technology ‘Open Access’, OMICS Group publishes 500 online open access scholarly journals in all aspects of Science, Engineering, Management and Technology journals. OMICS Group has been instrumental in taking the knowledge on Science & technology to the doorsteps of ordinary men and women. Research Scholars, Students, Libraries, Educational Institutions, Research centers and the industry are main stakeholders that benefitted greatly from this knowledge dissemination. OMICS Group also organizes 500 International conferences annually across the globe, where knowledge transfer takes place through debates, round table discussions, poster presentations, workshops, symposia and exhibitions.

## Slide 2: OMICS International Conferences
OMICS International is a pioneer and leading science event organizer, which publishes around 500 open access journals and conducts over 500 Medical, Clinical, Engineering, Life Sciences, Pharma scientific conferences all over the globe annually with the support of more than 1000 scientific associations and 30,000 editorial board members and 3.5 million followers to its credit.
OMICS Group has organized 500 conferences, workshops and national symposiums across the major cities including San Francisco, Las Vegas, San Antonio, Omaha, Orlando, Raleigh, Santa Clara, Chicago, Philadelphia, Baltimore, United Kingdom, Valencia, Dubai, Beijing, Hyderabad, Bengaluru and Mumbai.

## Slide 3: The Risk Management Plan and the first Marketing Authorisation Application - a practical approach
Peter Lannon, B.Pharm
Managing Director
Lanpharm Consulting
Surrey, United Kingdom
© 2015 Lanpharm Consulting

## Slide 4: Background
New MAA for late stage oncology indication (Orphan drug designation [ODD])
  In combination with chemotherapy followed by maintenance monotherapy
Company clinical programme had been stopped
  primary endpoints not met
Investigator Sponsored Study (ISS) showed efficacy in an indication that was not originally part of clinical development programme
Decision made to submit MAA
  Using ISS as the single pivotal study
  plus other studies in the company development programme
  pre-submission scientific discussion with EMA
© 2015 Lanpharm Consulting

## Slide 5: Project related challenges
Non-company sponsored study, therefore
  No control over study design
  No control over time and composition of data collected
    Time to onset was recorded as being at the next clinic visit
    Outcome was not collected for non-serious AEs
Resource limited
  Competition with other company MAAs (higher priority) for resource/senior stakeholder review
  Conflicting priorities – only 1 full FTE in safety department dedicated to the submission, others had other priorities to manage
© 2015 Lanpharm Consulting

## Slide 6: Project related challenges
Final decision to submit MAA not confirmed
But - tight project timelines which kept changing
Staff motivation
  Working on a submission with no confirmed decision to submit
Lack of company foresight and planning
  Due to inexperience
  Timing and sequence of higher level document draft/review/approval
  Review would be considerable based on volume of data
© 2015 Lanpharm Consulting

## Slide 7: Safety related challenges
Establishing the safety profile and presentation of safety data was complex
  Large amount of clinical data >5,000 patients
  Data not in the indication sought but from studies in other solid tumours
  Varying study designs
Lack of planning and foresight
Constantly changing priorities/timelines
Shifting of goal posts
© 2015 Lanpharm Consulting

## Slide 8: Safety related challenges
Establishing identified and potential risks
  Based on ISS or on company clinical programme?
  Different patient populations
Risk profile very similar to those of other drugs in class
  But large % of patients required dose modifications (dose reductions and dose pauses) and ultimately discontinued treatment due to toxicity
Two particular toxicities (non life-threatening) resulted in the most dose modifications
Reduction of discontinuations to increase benefit/risk
© 2015 Lanpharm Consulting

## Slide 9: Overcoming project challenges
Non-company sponsored study
  Need to validate ISS data
  Understand data and what is possible and realistic / scientifically credible
  Explain data capture and missing data early at pre-submission meeting and in HLDs as appropriate
Resources
  Almost always a problem so need to work smartly
  Being specific in requirements and precise in execution
  Utilise staff/consultants with previous MAA submission experience (where available)
  Careful planning and reactive to changes
© 2015 Lanpharm Consulting

## Slide 10: Overcoming project challenges
Project timelines
  Being adaptive and responsive
  Communication and education – sequence of documents –some dependent on prior approval of others
  Negotiation – some final text in the RMP dependant on other modules in the submission – agreement from senior stakeholders that final text in RMP would be added at the approval stage
  Manage expectations of team and stakeholders
© 2015 Lanpharm Consulting

## Slide 11: Overcoming safety related challenges
Complex and high volume of data
  Working smartly
  Creative application of scientific principles
  Presentation of ISS data
  Pool comprising of ISS study and other MAH sponsored combination studies
  Pool comprising MAH sponsored monotherapy studies
  Applying observations across the programme bearing in mind what was applicable to the indication being submitted
  Extensive literature review to try and characterise identified and potential risks due to limitations of ISS study
Identification of Identified and potential risks
  Initially based on data from pre-clinical programme
  Added to by what was observed in ISS study and across the MAH development programme.
  Finally looking at other class effects - identified as IIRs and IPRs
  Decision to include in RMP
© 2015 Lanpharm Consulting

## Slide 12: Overcoming safety related challenges
Decision whether to include additional risk minimisation measures (aRMMs) or not
Risk management to date
  Mostly well managed by investigator education and communication in protocols and in proposed SmPC
  Similar approach for post-marketing
Preparing possible aRMMs/scenarios/possibilities
  Benefit to patient
  Acceptable to EMA
  Achievable/cost effective and measurable
© 2015 Lanpharm Consulting

## Slide 13: Lessons learned - Suggestions
Always follow the science
Early planning
Stay focused
Communication
Transparency
Pragmatism
Creativeness
Reactivity/Flexibility
Resourceful
© 2015 Lanpharm Consulting

## Slide 14: Questions
© 2015 Lanpharm Consulting

## Slide 15: Contact Details
  Peter Lannon
  Director
  Lanpharm Consulting
  Tel: +44 (0) 7714202765
  Email: plannon@lanpharmconsulting.co.uk
  Website: http://www.lanpharmconsulting.co.uk
© 2015 Lanpharm Consulting

## Slide 16: Let us meet again..
We welcome you all to our future conferences of OMICS International
5th International Conference & Exhibition on Pharmacovigilance & Clinical Trials
On
September 19 - 21, 2016 at Vienna, Austria http://pharmacovigilance.pharmaceuticalconferences.com/